## Sheet1
User Story | To-Do | Inprogress | Done
As an election official, I want to get the election results of 500,000 ballots in 5 minutes. So I can publish the results in a timely manner. | add time calculater to record the task time |  | K
| improve the counting algorithm to calculate 500,000 ballots in 5 minutes |  | K
| create a testing task to test the time calculator |  | K
| create a testing task to counting algorithm’s performance |  | K
| document the performance of the counting algorithm | K
As an election official, I want to name and choose where to store the audit files in a GUI. So I can organize my audit file directory structure by inputting the path. | design a GUI for choosing directory | K
test the function of choosing directory
design a GUI for inputing file name
test the function of setting file name
document the default path and default file name
As a product manager, I want to make sure the CPL and OPL work properly and all bugs found so far fixed. So that the programs run smoothly and it doesn’t occur any error. | test the function of OPL
test the function of CPL
fix the bugs found so far
document the bugs currently cannot fix so far
As a user, I want to use csv file to obtain the infroamtion about seats, parties, candidates, and ballots so that it's more convientient for me to manipulate. | add function of reading CSV files to set format
test the function of reading format from CSV files
As a user, I want to use a graphic interface to search files, so that I can put voting file wherever I want | add a GUI for file search
test the function of file search through GUI
add function to read file from other directories through GUI
test the function of reading files from different directories through GUI
As an election official, I want to have the ballots input on the screen directly into the program and also stored to a CVS file. So the file can be saved as part of the audit. | finish the design documentation for ballot input through GUI
implement the function of inputing ballot through GUI
test the function of inputing ballot through GUI
finish the design documentation for saving ballot as a CSV file
implement the function of saving ballot as a CSV file
test the function of saving ballot as a CSV file
As an election official, I want to have the voting machines send the ballot information directly to the system. So I do not need to collect the ballot information manually. | finish the design documentation for sending ballot information from voting machine to the system
implement the function of sending ballot information from voting machine to the system
test the function of inputing sending ballot information from voting machine to the system
As an election official, I want to be prompted to enter the type of voting, OPL or CPL, along with all of the information needed to create the ballot at the start of an election. So I can easily run an election with the correct setting. | finish the design documentation for the GUI that prompts the election official to enter the setting of the voting at the start of an election
implement the GUI that prompts the election official to enter the setting of the voting at the start of an election
test the function of the GUI that prompts the election official to enter the setting of the voting at the start of an election
As an election official, I want to be able to stop the ability to collect additional ballots and the algorithms would then be run. So I have a strict control over the voting. | finish the design documentation for stoping collecting the ballots and initiate the election algorithms
implement the function of stoping collecting the ballots and initiate the election algorithms
test the function of stoping collecting the ballots and initiate the election algorithms